## Sheet1
Parental Controls and Device management on a home network
|  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29
|  | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TASK | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
PID
Basic Details
Degree suitability | bar: 2021-10-18 18 T to 2021-10-18 20 T; 2021-10-25 28 F to 2022-05-02 7 S
Project environment and problem | bar: 2021-10-18 18 T to 2021-10-18 20 T; 2021-10-25 28 F to 2022-05-02 7 S
Project aim and objectives | bar: 2021-10-18 18 T to 2021-10-18 20 T; 2021-10-25 28 F to 2022-05-02 7 S
Project deliverables
Project constraints
Project approach
Literature review plan | bar: 2021-10-18 20 T to 2021-10-18 21 F; 2021-10-25 28 F to 2022-05-02 7 S
Facilities and resources | bar: 2021-10-18 20 T; 2021-10-25 28 F to 2022-05-02 7 S
Log of risks | bar: 2021-10-18 20 T to 2021-10-18 23 S; 2021-10-25 28 F to 2022-05-02 7 S
Project plan | bar: 2021-10-18 20 T to 2021-10-18 23 S; 2021-10-25 28 F to 2022-05-02 7 S
Legal, ethical professional and social issues
Get PID Checked / Meeting
Literature review | bar: 2021-10-25 31 M to 2021-11-22 23 W
App review | bar: 2021-11-01 5 S to 2021-11-22 23 W
Research | bar: 2021-11-01 5 S to 2021-11-22 23 W
Requirements | bar: 2021-11-08 14 M to 2021-11-29 5 M
Gather User Requirements | bar: 2021-11-08 14 M to 2021-11-22 24 T
Create System Requirements | bar: 2021-11-22 23 W to 2021-11-29 5 M
Create priority list of requirements | bar: 2021-11-22 23 W to 2021-11-29 5 M
Design | bar: 2021-12-06 6 T to 2021-12-20 22 T; 2021-12-27 2 M to 2022-01-17 21 S
Methodology | bar: 2021-12-06 6 T to 2021-12-06 12 M
Architectural Design | bar: 2022-01-17 18 W to 2022-01-17 21 S
System Design (UML, Case Diagrams etc) | bar: 2022-01-10 16 M to 2022-01-17 19 T
Low-Fidelity Prototypes (Adobe XD) | bar: 2021-12-13 13 T to 2021-12-20 22 T
High-Fidelity Prototypes (axure) | bar: 2021-12-13 17 S to 2021-12-20 22 T; 2021-12-27 2 M to 2022-01-10 12 T
Design report (Font, colours, themes, usability) | bar: 2022-01-17 17 T to 2022-01-17 21 S
Implementation | bar: 2022-02-28 5 S to 2022-05-02 3 W
Release 1 - Website Blocking | bar: 2022-02-21 23 T to 2022-03-21 21 T
Release 2 - Dashboard user interface | bar: 2022-03-14 20 M to 2022-05-02 3 W
Release 3 - Device Management | bar: 2022-03-07 13 M to 2022-04-25 27 T
Report | bar: 2021-12-27 2 M to 2022-02-28 4 S; 2022-03-28 2 S to 2022-05-02 7 S
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Week 22 = [Week 21]+7
Week 23 = [Week 22]+7
Week 24 = [Week 23]+7
Week 25 = [Week 24]+7
Week 26 = [Week 25]+7
Week 27 = [Week 26]+7
Week 28 = [Week 27]+7
Week 29 = [Week 28]+7